## Sheet1
IPD - Activity Log Book
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Aug 2023 Week 1 | Collecting abandoned object image data | Started with generating dataset for object detection, counting and tracking | Generating and finding dataset
2 | 60004210212 | Aditya Dighe |  |  | Collecting crowded place image data |  | Generating and finding dataset
3 | 60004210214 | Mohit Dhatrak |  |  | Collecting abandoned object image data |  | Generating and finding dataset
4 | 60004210253 | Aradhya Sakalley |  |  | Collecting crowded place image data |  | Generating and finding dataset
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Aug 2023 Week 2 | Collecting abandoned object image data | Started with generating dataset for object detection, counting and tracking | Generating and finding dataset
2 | 60004210212 | Aditya Dighe |  |  | Collecting crowded place image data |  | Generating and finding dataset
3 | 60004210214 | Mohit Dhatrak |  |  | Collecting abandoned object image data |  | Generating and finding dataset
4 | 60004210253 | Aradhya Sakalley |  |  | Collecting crowded place image data |  | Generating and finding dataset
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Aug 2023 Week 3 | Collecting abandoned object image data | Started finding dataset for crowd density and abandoned object detection | Generating and finding dataset
2 | 60004210212 | Aditya Dighe |  |  | Collecting crowded place image data |  | Generating and finding dataset
3 | 60004210214 | Mohit Dhatrak |  |  | Collecting abandoned object image data |  | Generating and finding dataset
4 | 60004210253 | Aradhya Sakalley |  |  | Collecting crowded place image data |  | Generating and finding dataset
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Aug 2023 Week 4 | Collecting abandoned object image data | Started finding dataset for crowd density and abandoned object detection | Generating and finding dataset
2 | 60004210212 | Aditya Dighe |  |  | Collecting crowded place image data |  | Generating and finding dataset
3 | 60004210214 | Mohit Dhatrak |  |  | Collecting abandoned object image data |  | Generating and finding dataset
4 | 60004210253 | Aradhya Sakalley |  |  | Collecting crowded place image data |  | Generating and finding dataset
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Sept 2023 Week 1 | Working with python frameworks and libraries | Working with YOLOv8 and Open-CV to gather data points | Preprocessing the data
2 | 60004210212 | Aditya Dighe |  |  | Working with python frameworks and libraries |  | Preprocessing the data
3 | 60004210214 | Mohit Dhatrak |  |  | Working with python frameworks and libraries |  | Preprocessing the data
4 | 60004210253 | Aradhya Sakalley |  |  | Working with python frameworks and libraries |  | Preprocessing the data
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Sept 2023 Week 2 | Working with python frameworks and libraries | Working with YOLOv8 and Open-CV to gather data points | Preprocessing the data
2 | 60004210212 | Aditya Dighe |  |  | Working with python frameworks and libraries |  | Preprocessing the data
3 | 60004210214 | Mohit Dhatrak |  |  | Working with python frameworks and libraries |  | Preprocessing the data
4 | 60004210253 | Aradhya Sakalley |  |  | Working with python frameworks and libraries |  | Preprocessing the data
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Sept 2023 Week 3 | Working with python frameworks and libraries | Working with YOLOv8 and Open-CV to gather data points | Preprocessing the data
2 | 60004210212 | Aditya Dighe |  |  | Working with python frameworks and libraries |  | Preprocessing the data
3 | 60004210214 | Mohit Dhatrak |  |  | Working with python frameworks and libraries |  | Preprocessing the data
4 | 60004210253 | Aradhya Sakalley |  |  | Working with python frameworks and libraries |  | Preprocessing the data
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Sept 2023 Week 4 | Working with python frameworks and libraries | Working with YOLOv8 and Open-CV to gather data points | Preprocessing the data
2 | 60004210212 | Aditya Dighe |  |  | Working with python frameworks and libraries |  | Preprocessing the data
3 | 60004210214 | Mohit Dhatrak |  |  | Working with python frameworks and libraries |  | Preprocessing the data
4 | 60004210253 | Aradhya Sakalley |  |  | Working with python frameworks and libraries |  | Preprocessing the data
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Oct 2023 Week 1 | Implementing the different models | Implementing argparse and supervision for web-cam and zone annotator | Model development
2 | 60004210212 | Aditya Dighe |  |  | Implementing the different models |  | Model development
3 | 60004210214 | Mohit Dhatrak |  |  | Implementing the different models |  | Model development
4 | 60004210253 | Aradhya Sakalley |  |  | Implementing the different models |  | Model development
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Oct 2023 Week 2 | Implementing the different models | Implementing argparse and supervision for web-cam and zone annotator | Model development
2 | 60004210212 | Aditya Dighe |  |  | Implementing the different models |  | Model development
3 | 60004210214 | Mohit Dhatrak |  |  | Implementing the different models |  | Model development
4 | 60004210253 | Aradhya Sakalley |  |  | Implementing the different models |  | Model development
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Oct 2023 Week 3 | Implementing the different models | Building the CNN models for training the data | Model development
2 | 60004210212 | Aditya Dighe |  |  | Implementing the different models |  | Model development
3 | 60004210214 | Mohit Dhatrak |  |  | Implementing the different models |  | Model development
4 | 60004210253 | Aradhya Sakalley |  |  | Implementing the different models |  | Model development
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Oct 2023 Week 4 | Implementing the different models | Building the CNN models for training the data | Model development
2 | 60004210212 | Aditya Dighe |  |  | Implementing the different models |  | Model development
3 | 60004210214 | Mohit Dhatrak |  |  | Implementing the different models |  | Model development
4 | 60004210253 | Aradhya Sakalley |  |  | Implementing the different models |  | Model development
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Nov 2023 Week 1 | Testing the accuracy of the models | Annotating custom dataset using RoboFlow for parameter tuning and generating better efficacy | Accuracy improvements
2 | 60004210212 | Aditya Dighe |  |  | Testing the accuracy of the models |  | Accuracy improvements
3 | 60004210214 | Mohit Dhatrak |  |  | Testing the accuracy of the models |  | Accuracy improvements
4 | 60004210253 | Aradhya Sakalley |  |  | Testing the accuracy of the models |  | Accuracy improvements
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Nov 2023 Week 2 | Testing the accuracy of the models | Annotating custom dataset using RoboFlow for parameter tuning and generating better efficacy | Accuracy improvements
2 | 60004210212 | Aditya Dighe |  |  | Testing the accuracy of the models |  | Accuracy improvements
3 | 60004210214 | Mohit Dhatrak |  |  | Testing the accuracy of the models |  | Accuracy improvements
4 | 60004210253 | Aradhya Sakalley |  |  | Testing the accuracy of the models |  | Accuracy improvements
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Nov 2023 Week 3 | Testing the accuracy of the models | Annotating custom dataset using RoboFlow for parameter tuning and generating better efficacy | Accuracy improvements
2 | 60004210212 | Aditya Dighe |  |  | Testing the accuracy of the models |  | Accuracy improvements
3 | 60004210214 | Mohit Dhatrak |  |  | Testing the accuracy of the models |  | Accuracy improvements
4 | 60004210253 | Aradhya Sakalley |  |  | Testing the accuracy of the models |  | Accuracy improvements
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Nov 2023 Week 4 | Testing the accuracy of the models | Annotating custom dataset using RoboFlow for parameter tuning and generating better efficacy | Accuracy improvements
2 | 60004210212 | Aditya Dighe |  |  | Testing the accuracy of the models |  | Accuracy improvements
3 | 60004210214 | Mohit Dhatrak |  |  | Testing the accuracy of the models |  | Accuracy improvements
4 | 60004210253 | Aradhya Sakalley |  |  | Testing the accuracy of the models |  | Accuracy improvements
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Dec 2023 Week 1 | Discussing the combining of models | Building real time environment by integration | Developing user interface
2 | 60004210212 | Aditya Dighe |  |  | Discussing the combining of models |  | Developing user interface
3 | 60004210214 | Mohit Dhatrak |  |  | Discussing the combining of models |  | Developing user interface
4 | 60004210253 | Aradhya Sakalley |  |  | Discussing the combining of models |  | Developing user interface
1 | 60004210196 | Yuvraj Rasal | Pankaj Sonawane | Dec 2023 Week 2 | Discussing the combining of models | Building real time environment by integration | Developing user interface
2 | 60004210212 | Aditya Dighe |  |  | Discussing the combining of models |  | Developing user interface
3 | 60004210214 | Mohit Dhatrak |  |  | Discussing the combining of models |  | Developing user interface
4 | 60004210253 | Aradhya Sakalley |  |  | Discussing the combining of models |  | Developing user interface